## Legend
StreetBite V1.0 Manual QA workbook
How to use it
1. | Go to the TestCases sheet and run each case on a real device.
2. | Fill only the yellow cells: Actual Result, Status, Device, Bug ID, Executed On.
3. | Status must be Pass, Fail or Blocked (a dropdown is provided). A blank Status counts as Not Run.
4. | Every Fail needs a Bug ID from Jira (for example SB-12). Add the same bug to the DefectLog sheet.
5. | Traceability and Summary are formulas. Edit only the yellow cells there.
Status meanings
Pass | Actual result matches the expected result.
Fail | Actual result differs from the expected result. Log a bug.
Blocked | The case cannot be run (state cannot be reached, feature broken by another bug). Say why in Actual Result.
Severity (impact on the user)
Critical | App crashes, data loss, or login impossible.
High | A main feature is broken with no workaround.
Medium | A feature works but wrongly, or a workaround exists.
Low | Cosmetic issue or minor text problem.
Example of a filled row (format only, do not copy into TestCases)
TC ID | Actual Result | Status | Device | Bug ID | Executed On
TC_LOGIN_011 | "Enter a valid email address" shown under the email field. | Pass | Samsung SM-A366B | - | 2026-10-17
TC_HOME_009 | Badge stayed at 1 after the second tap. | Fail | Samsung SM-A366B | SB-12 | 2026-10-17

## TestCases
TC ID | Suite | Screen | Type | Req | Priority | Title | Preconditions | Steps | Test Data | Expected Result | Actual Result | Status | Device | Bug ID | Executed On
TC_LOGIN_001 | Login GUI | Login | GUI | R-01 | High | Splash screen with fade-in | App fully closed | 1. Launch the app. 2. Watch the first three seconds. | - | Logo, "StreetBite" and the tagline "Street food, found fast" fade in. After about two seconds the Login screen opens (or Home if a session exists). | The logo, 'StreetBite' and the tagline 'Street food, found fast' faded in, then the Login screen opened. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_002 | Login GUI | Login | GUI | R-13 | High | Login screen elements | Logged out | 1. Open the app and wait for Login. 2. Review the whole screen. | - | Logo, "Welcome back", the subtitle, Email and Password fields, the "Log in" button and the "New here? Create an account" link are visible and not cut off. | Logo, 'Welcome back', 'Log in to find your next bite', the Email and Password fields (password with eye icon), the 'Log in' button and the 'New here? Create an account' link are all visible and not cut off. (Screenshot_20261016_000056.jpg) | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_003 | Login GUI | Login | GUI | R-13 | Medium | Password visibility toggle | Logged out | 1. Type a password. 2. Tap the eye icon. 3. Tap it again. | Password: Test1234 | Password is masked by default, readable after the first tap and masked again after the second. | The password was masked at first, became visible after the first tap on the eye icon and was masked again after the second tap. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_004 | Login GUI | Login | GUI | R-10 | Medium | Login screen in dark mode | Dark mode switched on inside the app before signing out | 1. Sign out. 2. Review the Login screen. | - | Dark colours are applied, text and fields are readable, nothing has low contrast. | The Login screen used the dark colours; the text and fields were readable with no low-contrast areas. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_005 | Login GUI | Login | GUI | R-11 | Medium | Login screen in Arabic (RTL) | Arabic selected inside the app before signing out | 1. Sign out. 2. Review the Login screen. | - | All text is Arabic, the layout is right to left, no text overflows or is cut off. | The Login screen was fully Arabic and right to left, with no text clipped or overflowing. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_006 | Login Positive | Login | Positive | R-03 | High | Valid login opens Home | Registered account exists | 1. Enter the email and password. 2. Tap "Log in". | qa.tester@streetbite.test / Test1234 | The button shows a spinner, then Home opens with the greeting and meals. No error is shown. | The button showed a spinner, then Home opened with the greeting and the meals; no error was shown. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_007 | Login Positive | Login | Positive | R-04 | High | Session survives an app restart | Logged in successfully | 1. Close the app from recent apps. 2. Open it again. | - | Splash shows, then Home opens directly without asking for credentials. | After closing the app from Recent apps and reopening it, the Splash appeared and Home opened directly without asking for credentials. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_008 | Login Positive | Login | Positive | R-02 | Medium | Open Sign up and come back | Logged out | 1. Tap "New here? Create an account". 2. Review the screen. 3. Press back. | - | Sign up shows Full name, Email, Password and Confirm password fields and a "Sign up" button. Back returns to Login. | The Sign up screen opened with Full name, Email, Password, Confirm password and the 'Sign up' button; Back returned to Login. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_009 | Login Positive | Login | Positive | R-02 | High | Valid sign up logs the user in | Email not registered yet | 1. Open Sign up. 2. Fill every field. 3. Tap "Sign up". | Name: Test User Email: qa.new1@streetbite.test Password: Test1234 (both fields) | The Sign up screen closes by itself and Home opens with "Hi, Test". | The Sign up screen closed by itself and Home opened with 'Hi, Test'. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_010 | Login Negative | Login | Negative | R-03 | High | Empty fields | Logged out | 1. Leave both fields empty. 2. Tap "Log in". | - | "Please enter your email" and "Please enter a password" appear under the fields. The user stays on Login. | 'Please enter your email' and 'Please enter a password' appeared under the fields; the user stayed on Login. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_011 | Login Negative | Login | Negative | R-03 | Medium | Invalid email format | Logged out | 1. Enter a malformed email and a valid password. 2. Tap "Log in". | Email: abc Password: Test1234 | "Enter a valid email address" appears. No request is sent. | 'Enter a valid email address' appeared under the Email field when a malformed email ('g') was entered. (Screenshot_20261016_000114.jpg) | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_012 | Login Negative | Login | Negative | R-03 | High | Wrong password | Registered account exists | 1. Enter the registered email with a wrong password. 2. Tap "Log in". | Email: qa.tester@streetbite.test Password: WrongPass123 | A SnackBar shows "Wrong email or password." The user stays on Login and the fields keep their text. | A SnackBar 'Wrong email or password.' appeared; the user stayed on Login and both fields kept their text. (Screenshot_20261016_000347.jpg) | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_013 | Login Negative | Login | Negative | R-03 | Medium | Unregistered email | Logged out | 1. Enter an email that was never registered. 2. Tap "Log in". | Email: nobody@streetbite.test Password: WrongPass123 | A SnackBar shows "Wrong email or password." The user stays on Login. | A SnackBar 'Wrong email or password.' appeared and the user stayed on Login. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_014 | Login Negative | Login | Negative | R-02 | High | Sign up with lowercase first letter | Sign up screen open | 1. Enter a name starting with a lowercase letter. 2. Fill the other fields correctly. 3. Tap "Sign up". | Name: ahmed | "The first letter of your name must be capital" appears. No account is created. | With the name 'shahd khaled desouky' (lowercase first letter), 'The first letter of your name must be capital' appeared under Full name. (Screenshot_20261016_000216.jpg) | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_015 | Login Negative | Login | Negative | R-02 | High | Sign up with a short password | Sign up screen open | 1. Enter a five character password in both password fields. 2. Tap "Sign up". | Password: 12345 | "Password must be at least 6 characters" appears. | With a short password (2 characters), 'Password must be at least 6 characters' appeared under the Password field. (Screenshot_20261016_000216.jpg) | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_016 | Login Negative | Login | Negative | R-02 | Medium | Sign up with mismatched confirmation | Sign up screen open | 1. Enter different values in Password and Confirm password. 2. Tap "Sign up". | Password: Test1234 Confirm: Test12345 | "Passwords do not match" appears under Confirm password. | With different values in Password and Confirm password, 'Passwords do not match' appeared under Confirm password. (Screenshot_20261016_000216.jpg) | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_017 | Login Negative | Login | Negative | R-02 | Medium | Sign up with an existing email | Registered account exists | 1. Fill Sign up using the existing email. 2. Tap "Sign up". | Email: qa.tester@streetbite.test | A SnackBar shows "This email is already registered." The user stays on Sign up. | A SnackBar 'This email is already registered.' appeared and the user stayed on Sign up. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_018 | Login General Mobile | Login | General Mobile | R-03 | High | Login without internet | Airplane mode on | 1. Enter valid credentials. 2. Tap "Log in". | qa.tester@streetbite.test / Test1234 | A SnackBar shows "No internet connection. Check your network and try again." The app does not crash and the button becomes active again. | A SnackBar 'No internet connection. Check your network and try again.' appeared, the app did not crash and the button became active again. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_019 | Login General Mobile | Login | General Mobile | R-03 | Medium | Double tap on Log in | Internet on | 1. Enter valid credentials. 2. Tap "Log in" twice quickly. | qa.tester@streetbite.test / Test1234 | Only one request runs, the button is disabled with a spinner meanwhile, and Home opens once. | Only one login request ran: the button was disabled with a spinner while logging in and Home opened once. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_LOGIN_020 | Login General Mobile | Login | General Mobile | R-13 | Low | Android back button on Login | Logged out, Login screen visible | 1. Press the system back button. | - | The app closes cleanly with no crash or blank screen. | Pressing the system Back button on Login closed the app cleanly with no crash or blank screen. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_001 | Home GUI | Home | GUI | R-05 | High | Home screen elements | Logged in, meals loaded | 1. Review the whole Home screen from top to bottom. | - | Greeting and subtitle, banner, "Hot Offers", "Explore meals" grid, app bar with logo, language button and theme icon, and the four bottom tabs are visible. | Home shows the logo, the 'العربية' language button and the theme icon in the app bar, 'Hi, Shahd' with 'What are you craving today?', the featured banner, 'Hot Offers', the 'Explore meals' grid and the four bottom tabs (Home, Vendors, Cart, Profile). (Screenshot_20261016_000422.jpg, Screenshot_20261016_000522.jpg) | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_002 | Home GUI | Home | GUI | R-05 | High | Banner swipe | Home loaded | 1. Swipe the banner left and right. | - | Five featured meals are shown, each with image, name and category. The pager snaps to each card. | Five featured meals were shown, each with image, name and category; the pager snapped on each card. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_003 | Home GUI | Home | GUI | R-09 | High | Hot Offers list | Home loaded | 1. Scroll the Hot Offers row horizontally. 2. Count the cards. | - | Exactly five cards, each with image, name and price. The row scrolls smoothly. | The Hot Offers row scrolled smoothly and contained exactly five cards, each with image, name and price. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_004 | Home GUI | Home | GUI | R-08 | High | Two-column meals grid | Home loaded | 1. Scroll down to "Explore meals". 2. Check several cards, including long names. | - | Two columns. Each card shows image, name (up to two lines), category, price and the add button. No text overflows. | The grid shows two columns; each card has the image, name (two lines for long names), category, price in EGP and a cart button. No text overflows. (Screenshot_20261016_000522.jpg) | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_005 | Home GUI | Home | GUI | R-10 | Medium | Dark mode on Home | Home loaded | 1. Tap the theme icon. 2. Review Home. 3. Tap it again. | - | Home switches to dark with readable text, then back to light. | Home switched to dark mode with readable text, then returned to light mode. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_006 | Home GUI | Home | GUI | R-11 | High | Arabic and RTL on Home | Home loaded, English | 1. Tap the "العربية" button. 2. Review Home. 3. Tap "English". | - | All text is Arabic, the layout is right to left, prices end with ج.م, and the toggle now reads "English". Switching back restores English. | The app text turned Arabic (meal names and categories from the API stay in English), the layout was right to left, prices ended with the Arabic currency abbreviation and the toggle read 'English'; switching back restored English. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_007 | Home Positive | Home | Positive | R-06 | High | Meals load on first launch | Logged in, internet on | 1. Log in and watch Home. | - | A spinner shows first, then the banner, Hot Offers and the grid are filled with meals. | A spinner showed first, then the banner, Hot Offers and the grid were filled with meals. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_008 | Home Positive | Home | Positive | R-08 | High | Add a meal to the cart from the grid | Home loaded | 1. Tap the add button on any card. 2. Look at the Cart tab icon. | - | A SnackBar shows "<meal name> added to cart" and the cart badge shows 1. | A SnackBar '<meal name> added to cart' appeared and the cart badge showed 1. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_009 | Home Positive | Home | Positive | R-08 | Medium | Add the same meal twice | Cart empty | 1. Tap add twice on the same card. 2. Open the Cart tab. | - | Badge shows 2 and the cart has one line with "Qty: 2". | The badge showed 2 and the Cart had one line with 'Qty: 2'. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_010 | Home Positive | Home | Positive | R-12 | High | Open details from a grid card | Home loaded | 1. Tap a meal card. 2. Press back. | - | Meal Details open with image, name, category, origin and instructions. Back returns to Home. | Meal Details opened with image, name, category, origin and instructions; Back returned to Home. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_011 | Home Positive | Home | Positive | R-12 | Medium | Open details from banner and Hot Offers | Home loaded | 1. Tap a banner item. 2. Go back and tap a Hot Offers card. | - | Details open for the tapped meal each time. | Meal Details opened for the tapped meal, both from the banner and from Hot Offers. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_012 | Home Positive | Home | Positive | R-06 | Medium | Pull to refresh | Home loaded | 1. Pull down from the top of Home. | - | A refresh indicator shows, then the meals stay displayed. | A refresh indicator appeared and the meals stayed displayed. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_013 | Home Positive | Home | Positive | R-08 | Medium | Scroll the whole grid | Home loaded | 1. Scroll to the very bottom of the grid. | - | All meals are reachable, images load and the scroll stays smooth. | All meals were reachable at the bottom of the grid, the images loaded and the scroll stayed smooth. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_014 | Home Positive | Home | Positive | R-07 | High | Cached meals while offline | Meals loaded at least once | 1. Turn on airplane mode. 2. Force close the app. 3. Open it again. | - | Meals still appear from the cache and no error is shown. | Offline after a force close, the meals were shown from the cache but without their photos. (Screenshot: TC_HOME_014.png) | Fail | Samsung SM-A366B | SB-1 | 2026-10-16
TC_HOME_015 | Home Positive | Home | Positive | R-10 | Medium | Theme and language persist | Home loaded | 1. Switch to dark mode and Arabic. 2. Force close and reopen the app. | - | Dark mode and Arabic are still applied after the restart. | Dark mode and Arabic were still applied after force-closing and reopening the app. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_016 | Home Negative | Home | Negative | R-06 | High | Meal service unreachable with no cache | Meal API cannot be reached and no cache exists (if this state cannot be produced, mark Blocked and say why) | 1. Open Home in that state. 2. Tap "Try again" once the service is back. | - | A friendly message and a "Try again" button show instead of a crash. After retry the meals load. | Cannot be produced: meals are cached after the first load and the meal API is reachable. After clearing the app cache, going offline (internet off or Airplane mode) showed the same result as TC_HOME_014, and the meals appeared once the network was back. | Blocked | Samsung SM-A366B | - | 2026-10-16
TC_HOME_017 | Home Negative | Home | Negative | R-08 | Medium | Rapid taps on the add button | Cart empty | 1. Tap the add button ten times quickly. | - | The app stays responsive, the badge counts every tap, and SnackBars replace each other instead of stacking. | The app stayed responsive, the badge counted every tap and the SnackBars replaced each other instead of stacking. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_018 | Home Negative | Home | Negative | R-08 | Medium | Add to cart while offline | Home loaded, then airplane mode on | 1. Tap add on a card. | - | The meal is added to the cart, the SnackBar shows and the badge increases. | While offline, tapping add put the meal in the cart, the SnackBar appeared and the badge increased. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_019 | Home General Mobile | Home | General Mobile | R-05 | Medium | Background and resume | Home loaded | 1. Press the system Home button. 2. Wait one minute. 3. Reopen the app. | - | Home is still shown with its scroll position and no crash. | After one minute in the background, Home was shown at the same scroll position with no crash. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_020 | Home General Mobile | Home | General Mobile | R-05 | Medium | Rotate the device | Home loaded | 1. Rotate to landscape. 2. Rotate back. | - | No crash or overflow error. The layout adapts and returns to normal. | Rotating to landscape and back caused no crash or overflow error; the layout adapted and returned to normal. | Pass | Samsung SM-A366B | - | 2026-10-16
TC_HOME_021 | Home General Mobile | Home | General Mobile | R-05 | Low | Switch tabs and return | Home loaded, one item in cart | 1. Open Vendors, then Cart, then Home. | - | Home shows its meals without an error and the cart badge keeps its count. | Home showed its meals without an error after switching tabs and returning; the cart badge kept its count. | Pass | Samsung SM-A366B | - | 2026-10-16

## Traceability
Req ID | Requirement | Assignment section | Test case IDs | Total | Passed | Failed | Blocked | Not Run | Coverage status
R-01 | Splash/onboarding screen with a fade-in animation | Onboarding, Login and Sign Up | TC_LOGIN_001 | 1 | 1 | 0 | 0 | 0 | Covered and passed
R-02 | Sign-up validation: full name with capital first letter, email, password of at least six characters, password confirmation | Onboarding, Login and Sign Up | TC_LOGIN_008, TC_LOGIN_009, TC_LOGIN_014, TC_LOGIN_015, TC_LOGIN_016, TC_LOGIN_017 | 6 | 6 | 0 | 0 | 0 | Covered and passed
R-03 | Firebase Authentication login with friendly error messages | Onboarding, Login and Sign Up | TC_LOGIN_006, TC_LOGIN_010, TC_LOGIN_011, TC_LOGIN_012, TC_LOGIN_013, TC_LOGIN_018, TC_LOGIN_019 | 7 | 7 | 0 | 0 | 0 | Covered and passed
R-04 | Authentication state persists across app restarts | Onboarding, Login and Sign Up | TC_LOGIN_007 | 1 | 1 | 0 | 0 | 0 | Covered and passed
R-05 | Home screen responsive layout (MediaQuery) with a PageView banner of featured meals | Home Screen and Live Menu | TC_HOME_001, TC_HOME_002, TC_HOME_019, TC_HOME_020, TC_HOME_021 | 5 | 5 | 0 | 0 | 0 | Covered and passed
R-06 | Meals fetched from TheMealDB with Dio, with loading and friendly error states | Home Screen and Live Menu | TC_HOME_007, TC_HOME_012, TC_HOME_016 | 3 | 2 | 0 | 1 | 0 | In progress
R-07 | Meal data cached with shared_preferences and restored on restart | Home Screen and Live Menu | TC_HOME_014 | 1 | 0 | 1 | 0 | 0 | Failing
R-08 | Two-column meals grid with Add to Cart action and SnackBar | Home Screen and Live Menu | TC_HOME_004, TC_HOME_008, TC_HOME_009, TC_HOME_013, TC_HOME_017, TC_HOME_018 | 6 | 6 | 0 | 0 | 0 | Covered and passed
R-09 | Horizontal Hot Offers list with five items | Home Screen and Live Menu | TC_HOME_003 | 1 | 1 | 0 | 0 | 0 | Covered and passed
R-10 | Light and dark theme toggle connected to ThemeBloc | Home Screen and Live Menu | TC_LOGIN_004, TC_HOME_005, TC_HOME_015 | 3 | 3 | 0 | 0 | 0 | Covered and passed
R-11 | Runtime English/Arabic toggle with every visible string localized | English and Arabic Localization | TC_LOGIN_005, TC_HOME_006 | 2 | 2 | 0 | 0 | 0 | Covered and passed
R-12 | Meal details open from a meal card with the selected meal passed as an argument | Meal Details and Favourites | TC_HOME_010, TC_HOME_011 | 2 | 2 | 0 | 0 | 0 | Covered and passed
R-13 | Login screen layout: logo, fields, password visibility and sign-up link | Onboarding, Login and Sign Up | TC_LOGIN_002, TC_LOGIN_003, TC_LOGIN_020 | 3 | 3 | 0 | 0 | 0 | Covered and passed
Note: the Test case IDs column is plain text built from the Req column in TestCases. If you change a Req value there, update this column by hand. All counts are live formulas.

## DefectLog
Jira key | Title | Linked TC | Severity | Priority | Status | Found on | Screenshot file
SB-1 | Cached meals are shown without photos when the phone is offline | TC_HOME_014 | Medium | Low | Open | 2026-10-16 | TC_HOME_014.png

## Summary
Test execution summary and closure
Scope and environment
Application | StreetBite V1.0 (1.0.0+1)
Build under test | Debug APK
Primary device | Samsung SM-A366B (real device)
Secondary device | Android emulator
Tester | Shahd Zain
Test period | 2026-10-16 to 2026-10-18
Defect tracker | Jira
Yellow cells above are assumptions taken from the project setup. Edit them if they changed.
Execution results
Group |  | Total | Pass | Fail | Blocked | Not run
All cases |  | 41 | 39 | 1 | 1 | 0
Screen: Login |  | 20 | 20 | 0 | 0 | 0
Screen: Home |  | 21 | 19 | 1 | 1 | 0
Type: GUI |  | 11 | 11 | 0 | 0 | 0
Type: Positive |  | 13 | 12 | 1 | 0 | 0
Type: Negative |  | 11 | 10 | 0 | 1 | 0
Type: General Mobile |  | 6 | 6 | 0 | 0 | 0
Pass rate (of executed cases) |  | 95.12%
Executed (Pass + Fail + Blocked) |  | 100%
Defects (from DefectLog)
Severity |  | Total | Not closed
Critical |  | 0 | 0
High |  | 0 | 0
Medium |  | 1 | 1
Low |  | 0 | 0
Exit criteria
Criterion | Target | Actual | Result
Minimum pass rate | 90% | 95.12% | Met
All planned cases executed | 100% | 100% | Met
No open Critical or High defects | 0 | 0 | Met
Every Fail has a Bug ID | 0 | 0 | Met
Every requirement has at least one case | 0 | 0 | Met
Overall exit decision |  | Exit criteria met
Closure summary (fill in after execution)
Overall outcome | 41 cases were executed on the Samsung SM-A366B: 39 Pass, 1 Fail and 1 Blocked (pass rate 95.1%). All exit criteria are met.
Main findings | Login (validation, wrong and unknown credentials, session persistence, offline message) and Home (banner, Hot Offers, grid, cart, theme and language, cache) behave as specified. One defect was found: SB-1, cached meals are shown without photos when the phone is offline (TC_HOME_014). The smoke checklists from the Test Plan (Meal Details, Cart, Vendor Map and Profile) were also run on the Samsung SM-A366B and worked as described; no defects were found there.
Open risks and known issues | SB-1 is open (Medium severity, Low priority). TC_HOME_016 (meal service down with no cache) is Blocked because meals are cached after the first load and the meal API is reachable, so that error state could not be produced. Only one physical device was used.
Recommendation | Ready for the beta release. Cache the meal photos so that Home looks complete offline, then re-test TC_HOME_014 on the same device.
Sign-off (name and date) | Name : shahd zain , Date : 10/18/2026